## Instructions
CONSTRUCTION CONTRACTOR INVOICE INSTRUCTIONS |  |  | NJSDA 803
ITEMS 1 THROUGH 10 ARE TO BE COMPLETED BY CONTRACTOR
1 | Contractor Invoice Number
Contractor invoice, billing number, or any other identification for reference purposes.
2 | Contractor Identification Number
Federal identification number listed on your W9 form.
3 | NJSDA Contract Number
The contract number.
4 | NJSDA Package Number
The package number.
5 | Billing Period
The time period for the work completed.
6 | Package Name
The package name.
7 | Contractor Name and Address
The name of the individual or company that appears on the NJSDA CONTRACT.
8 | Submissions Checklist
Mark the items on the list that correspond to the attachments included with this invoice.
9 | Contract Summary (Only data entry fields highlighted in blue must be completed)
Original Contract Amount: Enter original contract value.
Approved/Executed Change Orders: Enter cumulative value of all approved/executed change orders as listed on the Form 810 submitted for this billing period. Do not include pending modifications.
Retainage % This Period: Enter the retainage percentage for the billing period of work completed. If the retainage percentage has not been changed through submission of the appropriate documentation then this percentage is located in the General Terms & Conditions listed in the contract.
Previously Completed and Stored: Enter the Total Completed and Stored to Date amount listed on the previously billed invoice for this contract.
Total Completed and Stored This Period: Enter the total amount of work being billed for this period as listed on the Form 810 submitted for this billing period.
Total Prior Retainage: Enter Total Retainage amount listed on the previously billed invoice for this contract. This amount is the cumulative value of all retainage for the contract prior to the current invoice.
10 | Contractor Declaration
Contractor must read and fill out the items of the declaration.

## NJSDA Form 803
|  | CONSTRUCTION CONTRACTOR INVOICE | [9 empty] | NJSDA 803
1. Contractor Invoice No. |  | 2. Contractor Identification No. |  |  |  | 3. NJSDA Contract No. |  |  | 4. NJSDA Package No.
5. Billing Period |  |  |  | 8. Submissions Checklist
From: |  | To: |  |  | A. | SDA Form 803 Construction Contractor Invoice
[5 empty] | B. | SDA Form 803A Construction Contractor Invoice – Project Breakout
6. Package Name |  |  |  |  | C. | SDA Form 803B or 803C Sub-Contractor / Consultant Verification Form
[5 empty] | D. | SDA Form 810 Schedule of Amounts of Monthly Payments to Contractor
[5 empty] | E. | SDA Form 811 Certification Of Prime Contractor
[5 empty] | F. | SDA Form 812 Agreement & Bill of Sale Certification For Stored Material
[5 empty] | G. | SDA Form 813 Contractor’s Summary of Stored Materials
7. Contractor Name and Address |  |  |  |  | H. | SDA Form 814 Consent Of Surety to Reduction in or Partial Release of Retainage
[5 empty] | I. | SDA Form 820 Partial Waiver and Release
Name: |  |  |  |  | J. | Progress Photots and Project Schedule
Address: |  |  |  |  | K. | Certificate of Insurance
9. Contract Summary
Original Contract Amount |  |  |  |  | $ | 0
Approved/Executed Change Orders |  |  |  |  | $ | 0
Current Approved Contract Amount | [8 empty] | $ | 0
Retainage % This Period
Previously Completed and Stored |  |  |  |  | $ | 0
Total Completed and Stored This Period |  |  |  |  | $ | 0
Total Completed and Stored to Date |  |  |  |  | $ | 0
Retainage This Period |  |  |  |  | $ | 0
Total Prior Retainage | [8 empty] | $ | 0
Total Retainage | [8 empty] | $ | 0
Total Earned Less Retainage | [8 empty] | $ | 0
Previous Billed To Date Less Retainage | [8 empty] | $ | 0
Current Payment Due | [8 empty] | $ | 0
Remaining Balance | [8 empty] | $ | 0
10. Contractor Declaration
I certify that this invoice is accurate and correct in all its particulars, that the described goods or services have been furnished or rendered in accordance with the contract documents, that no bonus has been given or received on account of said invoice, that all amounts have been paid by the Contractor for Work for which previous payments were issued by the Authority and received by the Contractor, and that the Current Payment Due, as shown above, is now due.
Signature | [6 empty] | Print Name
Title | [6 empty] | Date
11. CERTIFICATION BY PMF/CM | [5 empty] | 12. CERTIFICATION BY SDA PROGRAM OFFICER
Based on on-site observations and the data comprising the above invoice, I certify that to the best of my knowledge, information, and belief, the work has progressed as indicated, the quality of the work is in accordance with Contract Documents, the above invoice conforms with the “Pencil-Session” invoice that was reviewed and approved by the Contractor, Design Consultant and the PMF/CM and therefore the Contractor is entitled to Current Payment Due. | [5 empty] | As an authorized representative of the Authority, I certify this invoice to be correct and that, to the best of my knowledge, all work covered by this invoice has been completed. Payment is approved in the amount noted.
Authorized Signature: |  |  | Date: |  |  | Authorized Signature: |  |  |  |  | Date:
Print Name: | [5 empty] | Print Name:
ADDITIONAL SDA OPERATING AUTHORITY SIGNATURES | [5 empty] | ADDITIONAL SDA OPERATING AUTHORITY SIGNATURES
[6 empty] | Authorized Signature: |  |  |  |  | Date:
Print Name:
Authorized Signature: |  |  | Date: |  |  | Authorized Signature: |  |  |  |  | Date:
Print Name: | [5 empty] | Print Name:
Authorized Signatures: |  |  | Date: |  |  | Authorized Signature: |  |  |  |  | Date:
Print Name: | [5 empty] | Print Name:
[6 empty] | 0 |  | This calculation is the TOTAL RETAINAGE using the retainage % based off of the TOTAL PRIOR RETAINAGE. Therefore if TOTAL PRIOR RETAINAGE is greater that this figure there has been a reduction in the RETAINAGE % this period.
#DIV/0!
Note on F27: Enter retainage percentage for this billing period. If the retainage percentage has not been reduced through submission of the appropriate documentation then this percentage is located in the General Terms & Conditions listed in the contract.
Note on N23: Enter original contract value.
Note on N24: Enter cumulative value of all approved change orders as listed on the Form 810 submitted for this billing period.
Note on N28: Enter the Total Completed and Stored to Date amount listed on the previously billed invoice for this contract.
Note on N29: Enter the total amount of work being billed for this period as listed on the Form 810 submitted for this billing period.
Note on S32: Enter Total Retainage amount listed on the previously billed invoice for this contract. This amount is the cumulative value of all retainage for the contract prior to the current invoice.